## Josh Welicky
Date | User Story | Hours Worked | Description
2025-08-29 | NA | 0.75 | Initial meeting with GTA supervisor. Overviewed expectations and established plan for next meeting.
2025-09-02 | NA | 1 | Meeting with project team. See meeting1.txt for more details.
2025-09-04 | NA | 2 | Created and disbursed the Work Log, Project Estimates document. Worked on the preliminary listing of the project requirements based on the project description. Added some additional requirements as well. This occurred over a few hours, but I was only really working for two.
2025-09-05 | NA | 0.75 | Meeting with GTA supervisor. Provided weekly project update.
2025-09-08 | NA | 1.5 | Reworked our estimates document to use the Use Case Points technique. Integrated User Story number into the work logs.
2025-09-09 | NA | 0.5 | Created estimates using the User Story technique, since I am not sure which methodology they prefer.
2025-09-09 | NA | 1 | Meeting with project team. See meeting2.txt for more details.
2025-09-11 | NA | 1.5 | Conducted a review of the current implementation. Found a number of concerns that I will note and address during the friday meeting.
2025-09-12 | 5.1 | 0.08 | Implemented a controls message that prints before requesing a command every time.
2025-09-12 | NA | 2 | Further reviewed the code, and compared it both to our previous implementation and user requirements. Evaluated the necessity of some extraneous features. Began work on converting the older implementation into something more modular.
2025-09-12 | NA | 0.5 | Meeting with GTA supervisor. Provided weekly project update.
2025-09-16 | NA | 0.5 | Meeting with project team. See meeting3.txt for more details.
2025-09-16 | 1.1 | 0.1 | Transferred board generation to a class-based structure.
2025-09-16 | 1.2 | 0.1 | Integrated initial mine protections into the class-based structure.
2025-09-16 | 2.1 | 0.1 | Integrated standard cell uncovering into the class-based structure.
2025-09-16 | 2.2 | 0.1 | Adapted the recursive uncovering code into the class-based structure.
2025-09-16 | 2.3 | 0.1 | Moved game over code into the class-based structure.
2025-09-16 | 2.4 | 0.1 | Added status checking code into the class-based structure.
2025-09-16 | 2.5 | 0.1 | Brought the emojis into the class-based structure.
2025-09-16 | 3.1 | 0.1 | Integrated the flagging feature into the class-based structure.
2025-09-16 | 3.2 | 0.1 | Adjusted unflagging as well.
2025-09-16 | 4.1 | 0.1 | Integrated the existing board printing and status checking into exisiting methods.
2025-09-16 | 5.2 | 0.1 | Brought the startup message into the class-based program.
2025-09-17 | NA | 2 | Drafted initial Software Architecture document (basic structure, and components description section).
2025-09-18 | NA | 1 | Continued drafting the Software Architecture document (added introduction and data flow discussion/diagram).
2025-09-19 | NA | 0.5 | Corrected final project design diagram and added it to the Software architecture document.
2025-09-19 | NA | 0.75 | Added more comments to the code, and updated Software Architecture document with timing feature.

## Mark Kitchin
Date | User Story | Hours Worked | Description
2025-08-29 | NA | 0.75 | Initial meeting with GTA supervisor. Overviewed expectations and established plan for next meeting.
2025-09-02 | NA | 1 | Meeting with project team. See meeting1.txt for more details.
2025-09-05 | NA | 0.75 | Meeting with GTA supervisor. Provided weekly project update.
2025-09-09 | NA | 1 | Meeting with project team. See meeting2.txt for more details.
2025-09-16 | NA | 0.5 | Meeting with project team. See meeting3.txt for more details.
2025-09-09 | NA | 2 | Tested initial implementation, before the code was converted into a modular format
2025-09-11 | NA | 1 | Experimented with user profile storage implementation, which was removed later | 1
2025-09-18 | NA | 1 | Conducted a code review of the implementation with classes, and discovered a potential issue with array implementation
2025-09-19 | NA | 1 | Full code and documentation review, stress tested the code pre demo

## Max Biundo
Date | User Story | Hours Worked | Description
2025-08-29 | NA | 0.75 | Initial meeting with GTA supervisor. Overviewed expectations and established plan for next meeting.
2025-09-02 | NA | 1 | Meeting with project team. See meeting1.txt for more details.
2025-09-04 | NA | 4 | Creating the class diagram for the project
2025-09-05 | NA | 0.75 | Meeting with GTA supervisor. Provided weekly project update.
2025-09-09 | NA | 1 | Meeting with project team. See meeting2.txt for more details.
2025-09-12 | 4.2 | 1 | Added basic timer functionality
2025-09-12 | NA | 0.5 | Meeting with GTA supervisor. Provided weekly project update.
2025-09-16 | NA | 0.5 | Meeting with project team. See meeting3.txt for more details.
2025-09-19 | NA | 1 | Updated class diagram to more accurately convey project architecture
2025-09-19 | 4.2 | 0.5 | Updated timer functionality

## Bisshoy Bhattacharjee
Date | User Story | Hours Worked | Description
2025-08-29 | NA | 0.75 | Initial meeting with GTA supervisor. Overviewed expectations and established plan for next meeting.
2025-09-02 | NA | 1 | Meeting with project team. See meeting1.txt for more details.
2025-09-05 | NA | 0.75 | Meeting with GTA supervisor. Provided weekly project update.
2025-09-05 | NA | 0.5 | Reviewed code and added the game to accept both lower and uppercase input
2025-09-09 | NA | 1 | Meeting with project team. See meeting2.txt for more details.
2025-09-11 | 7.1 | 2 | Implemented profile making and autosave feature (feature was later dropped for time)
2025-09-11 | 2.3 | 0.5 | Program uncovers grid and shows bomb location
2025-09-11 | 5.2 | 0.5 | Game now shows rule at the beginning of the game and changed bombs and flag with emojis
2025-09-12 | NA | 0.5 | Meeting with GTA supervisor. Provided weekly project update.
2025-09-16 | NA | 0.5 | Meeting with project team. See meeting3.txt for more details.
2025-09-17 | NA | 1 | Added comments explaining each function and major blocks of code

## Gavin Billinger
Date | User Story | Hours Worked | Description
2025-08-29 | NA | 0.75 | Initial meeting with GTA supervisor. Overviewed expectations and established plan for next meeting.
2025-09-02 | NA | 1 | Meeting with project team. See meeting1.txt for more details.
2025-09-03 | NA | 0.75 | Drafted initial design thoughts in a small document for team to see
2025-09-05 | 8 | 1.5 | Developed board generation implementation concept
2025-09-05 | NA | 0.75 | Meeting with GTA supervisor. Provided weekly project update.
2025-09-08 | 1.1,1.2,4.1, 2.1 | 1.25 | Implemented non-colliding, first user input and general user input.
2025-09-09 | 3.1,3.2, 2.2, 2.4 | 1.25 | Implemented error handling, game loss scenario, flag functionality and space propagation
2025-09-09 | 4.1 | 0.25 | Implemented win condition
2025-09-09 | 1.2 | 0.25 | Polished first click implementation
2025-09-09 | NA | 1 | Meeting with project team. See meeting2.txt for more details.
2025-09-12 | NA | 0.5 | Meeting with GTA supervisor. Provided weekly project update.
2025-09-16 | NA | 0.5 | Meeting with project team. See meeting3.txt for more details.
2025-09-18 | NA | 0.5 | Performed some testing and code corrections.
2025-09-19 | NA | 0.5 | Performed last minute testing and made minor adjustments to code.